SUPPLY MANAGEMENT SYSTEM

Task Register

Addendum 29 - SCM Commercial Enablement

Business Partners | Sales Orders | Fulfillment | Invoicing | Customer Finance

Implementation Task Breakdown for Claude Code

Version 1.3 - Logistics-Aligned (Delivery Orders + IStockReservationService)

| Property | Value |
| --- | --- |
| Document ID | SMS-TR-ADD-029 |
| FSD Reference | SMS-FSD-ADD-029 v1.3 |
| Version | 1.0 |
| Date | 2026-09-19 |
| Classification | Internal - Development |
| Total Tasks | 68 |
| Total Estimated Effort | 30 Dev Days (240 Hours) |
| Architecture | .NET 8 / EF Core 8 / SQL Server 2022 / React 18 |
| Status | Ready for Execution |

# Table of Contents

1. Executive Summary & Scope

2. Task Register Legend

3. Phase 1 — Foundation (Business Partner Migration)

4. Phase 2 — Product & Pricing

5. Phase 3 — Sale Order Core

6. Phase 4 — Availability, Reservation & Email

7. Phase 5 — Back-to-Back PO & trace_id Linkage

8. Phase 6 — Fulfillment (Delivery Orders Integration)

9. Phase 7 — Sales Invoicing & Customer Finance

10. Phase 8 — Product Ledger & Inventory Impact

11. Phase 9 — Reports & Frontend

12. Phase 10 — Integration Testing & Acceptance

13. Dependency Graph

14. Effort Summary by Phase

15. Risk Register

16. Migration Script Execution Order

# 1. Executive Summary & Scope

This task register decomposes FSD Addendum 29 v1.3 (SCM Commercial Enablement) into granular, independently executable tasks. Each task maps directly to a section in the FSD, has explicit dependencies, estimated hours, and linked test case IDs.

Key alignment principle: This addendum reuses the existing logistics infrastructure (delivery_orders, IStockReservationService, pick/pack/goods-issue, carrier integration) rather than creating parallel structures. Tasks are structured accordingly — extending existing code rather than greenfield creation.

## Scope Boundaries

- IN SCOPE: Business Partner migration, Sale Orders, Stock Reservation (SALES_ORDER source), Back-to-Back PO, Drop Ship, Self-Pickup, Sales Invoicing, Customer Ledger, Product Ledger, 10 Sales Reports, Email Intimation, PO-SO trace_id linkage

- IN SCOPE (Integration): Extend existing delivery_orders, IStockReservationService, GoodsIssueService, pick lists, pack API, carrier booking for sales fulfillment

- OUT OF SCOPE: Carrier onboarding (already built), Warehouse setup (already built), Supplier Scorecard (Addendum 23), Supplier Rate Cards (Addendum 28), Returns/Credit Notes (future addendum)

## Technical Stack

| Component | Technology |
| --- | --- |
| Backend | ASP.NET Core 8 / C# 12 / .NET 8 LTS |
| Database | SQL Server 2022 with EF Core 8 Code-First |
| ORM | EF Core 8 with dotnet ef migrations |
| Auth | ASP.NET Core Identity + JWT (org_id claim for multi-tenancy) |
| Background Jobs | Hangfire (hangfire schema in SQL Server) |
| PDF Generation | QuestPDF |
| Mapping | AutoMapper |
| Validation | FluentValidation |
| Events | MediatR |
| Frontend | React 18 + Vite + TypeScript |
| Multi-Tenancy | Shared DB, org_id discriminator, EF Core HasQueryFilter |

# 2. Task Register Legend

| Field | Description |
| --- | --- |
| Task ID | Unique identifier: A29-{phase}-{seq} (e.g., A29-P1-01) |
| Task Title | Concise action-oriented title |
| Description | What the task produces — entity, service, API, migration, or test |
| FSD Ref | Section reference in SMS-FSD-ADD-029 v1.3 |
| Schema(s) | Database schema(s) affected |
| Depends On | Task IDs that must be completed first |
| Est. Hours | Estimated implementation hours (including unit tests) |
| Test IDs | Linked acceptance test case IDs from FSD Section 17 |

## Task Type Color Coding

| Type | Description | Naming Pattern |
| --- | --- | --- |
| Migration | EF Core database migration | ...migration / ...rename / ...add |
| Entity | C# entity class, EF configuration, DTO, AutoMapper profile | ...entity / ...model |
| Service | Business logic service layer | ...service / ...logic |
| API | Controller endpoints with FluentValidation | ...api / ...endpoints |
| Integration | Extending existing service/entity for new source type | ...extend / ...integrate |
| Frontend | React components, pages, API hooks | ...ui / ...page / ...component |
| Test | Integration test, acceptance test | ...test / ...verify |
| Hangfire | Background job definition and registration | ...job / ...worker |

## Priority Levels

| Priority | Description |
| --- | --- |
| P0 — Critical Path | Blocks multiple downstream tasks. Must be completed first. |
| P1 — High | Required for core functionality. Part of the main execution flow. |
| P2 — Medium | Important but has limited downstream dependencies. |
| P3 — Low | Enhancement, reporting, or polish. Can be deferred. |

# 3. Phase 1 — Foundation (Business Partner Migration)

Priority: P0 — Critical Path | Estimated: 32 Hours (4 Days) | FSD Sections: 1.1–1.7

This phase renames Suppliers to BusinessPartners and adds carrier/customer/service-provider capabilities. Zero data loss. All existing FK references updated.

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P1-01 | Rename Suppliers → BusinessPartners (Migration) | EF Core migration: sp_rename [suppliers.Suppliers] to [suppliers.BusinessPartners]. Rename PK column supplier_id → partner_id. Update all FK references across procurement, inventory, finance schemas. | §1.1 | suppliers, procurement, inventory, finance | — | 4 | TC-01 |
| A29-P1-02 | Add Partner Type Flags & Carrier/Service Fields (Migration) | Add columns: partner_type NVARCHAR(20), is_vendor BIT, is_customer BIT, is_carrier BIT, is_service_provider BIT, vehicle_types, service_categories, credit_limit, payment_terms_days. UPDATE existing rows SET partner_type='VENDOR', is_vendor=1. | §1.2, §1.3 | suppliers | A29-P1-01 | 3 | TC-01 |
| A29-P1-03 | BusinessPartner Entity & EF Configuration | C# entity: BusinessPartner with partner_type enum, four boolean flags. EF config: HasQueryFilter(p => p.OrgId == _orgId). AutoMapper profile: BusinessPartnerDto ↔ BusinessPartner. FluentValidation: partner_type must match flag combination. | §1.2, §1.3 | suppliers | A29-P1-02 | 4 | TC-01, TC-12 |
| A29-P1-04 | BusinessPartner Repository & Service | IBusinessPartnerRepository + BusinessPartnerService. Auto-compute partner_type from boolean flags on save. Filter methods: GetVendors(), GetCustomers(), GetCarriers(), GetServiceProviders(). Soft delete support. | §1.3–§1.5 | suppliers | A29-P1-03 | 4 | TC-01, TC-02, TC-03 |
| A29-P1-05 | BusinessPartner API Controller | PartnersController: GET/POST/PUT/DELETE /api/partners with filter params (type, is_vendor, is_customer, is_carrier, is_service_provider, active, search). Backward-compat aliases: /api/suppliers, /api/customers, /api/carriers, /api/service-providers. | §1.6, §1.7 | suppliers | A29-P1-04 | 4 | TC-01, TC-02, TC-03, TC-12 |
| A29-P1-06 | Update All Existing References (Supplier → Partner) | Rename SupplierLedger → PartnerLedger. Update all service/repository/controller references from Supplier to BusinessPartner. Update Scorecard (Add23) and RateCard (Add28) to filter by is_vendor=1. Verify all procurement flows unchanged. | §1.7 | suppliers, procurement, finance | A29-P1-05 | 6 | TC-01 |
| A29-P1-07 | BusinessPartner Unit & Integration Tests | Test: CRUD operations, partner_type auto-computation from flags, backward-compat /api/suppliers alias returns only vendors, FK integrity after rename, multi-tenant isolation. | §1.1–§1.7 | suppliers | A29-P1-06 | 4 | TC-01, TC-02, TC-03, TC-12 |
| A29-P1-08 | BusinessPartner Frontend Pages | React: Partners list page with type filter tabs (All/Vendors/Customers/Carriers/Service Providers). Partner create/edit form with dynamic fields based on type flags. Partner detail page with ledger tab. | §1.6 | — | A29-P1-05 | 3 | — |

# 4. Phase 2 — Product & Pricing

Priority: P1 — High | Estimated: 16 Hours (2 Days) | FSD Sections: 2.1–2.4

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P2-01 | Add Default Supplier to ProductVariants (Migration) | Add columns to inventory.ProductVariants: default_supplier_id BIGINT NULL FK to BusinessPartners(is_vendor=1), lead_time_days INT NULL. | §2.1 | inventory | A29-P1-02 | 1 | — |
| A29-P2-02 | Create PricingRules Table (Migration) | Create inventory.PricingRules: pricing_rule_id, org_id, variant_id, partner_id (NULL=all), price_type (SELLING¦COST¦PROMOTIONAL¦CONTRACT), min_qty, max_qty, unit_price, currency_code, effective_from/to, is_active. HasQueryFilter on org_id. | §2.2 | inventory | A29-P1-02 | 2 | — |
| A29-P2-03 | PricingRule Entity, Service & Price Resolution Logic | IPricingService with ResolveSalePrice(variantId, partnerId, qty, date) implementing 5-priority resolution: CONTRACT → PROMOTIONAL → Partner SELLING → Default SELLING → Variant.selling_price. ResolvePurchasePrice: RateCard → LastPO → Variant.purchase_price. | §2.3, §2.4 | inventory | A29-P2-02 | 5 | — |
| A29-P2-04 | PricingRules API Endpoints | PricingRulesController: CRUD /api/pricing-rules. GET /api/pricing-rules/resolve?variantId&partnerId&qty for price preview. Filter by variant, partner, type, active. | §2.2–§2.4 | inventory | A29-P2-03 | 3 | — |
| A29-P2-05 | Pricing Unit Tests | Test 5-priority price resolution with edge cases: no rules, expired rules, overlapping qty ranges, partner-specific vs default, contract vs promotional priority. | §2.3, §2.4 | inventory | A29-P2-03 | 3 | — |
| A29-P2-06 | Pricing Frontend (Admin) | React: Pricing rules CRUD page on Product Variant detail. Price type selector, date range pickers, quantity tiers. Price preview calculator. | §2.2 | — | A29-P2-04 | 2 | — |

# 5. Phase 3 — Sale Order Core

Priority: P0 — Critical Path | Estimated: 24 Hours (3 Days) | FSD Sections: 3.1–3.5, 4.1–4.2

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P3-01 | Create SUPPLY_DEPT_ADMIN Role (Migration + Seed) | Create role in auth schema. Assign permissions: sale_order_config_read, sale_order_config_write. IT_ADMIN gets read-only. Seed role in migration. | §3.1 | auth | A29-P1-02 | 2 | — |
| A29-P3-02 | Create SaleOrderConfig Table (Migration) | Create demand.SaleOrderConfig: config_id, org_id (one per org), auto_po_enabled, supplier_selection_mode, auto_po_approval_mode, drop_ship_enabled, self_pickup_enabled, default_fulfillment_mode, reservation_ttl_hours, partial_fulfillment_allowed, email_intimation_enabled, intimation_department_id, intimation_cc_emails, shipment_required_default. HasQueryFilter on org_id. | §3.2 | demand | A29-P3-01 | 2 | — |
| A29-P3-03 | SaleOrderConfig Entity, Service & API | SaleOrderConfigService: GetConfig(orgId), UpdateConfig(orgId, dto). Audit trail on every change. API: GET/PUT /api/sale-order-config (SUPPLY_DEPT_ADMIN only for write). GET /api/sale-order-config/audit. | §3.2–§3.5 | demand, auth | A29-P3-02 | 3 | — |
| A29-P3-04 | Create SaleOrders & SaleOrderLines Tables (Migration) | Create demand.SaleOrders: sale_order_id, org_id, so_number, partner_id (is_customer=1), order_date, expected_delivery_date, currency_code, subtotal, tax_amount, discount_amount, grand_total, status (DRAFT¦CONFIRMED¦PARTIALLY_FULFILLED¦FULFILLED¦INVOICED¦CLOSED¦CANCELLED), requires_shipment, delivery_mode (SHIP¦SELF_PICKUP), shipping_address_id FK to logistics.addresses, trace_id UNIQUEIDENTIFIER, is_deleted. Create demand.SaleOrderLines: so_line_id, sale_order_id, variant_id, quantity, unit_price, discount_percent, tax_percent, line_total, fulfilled_qty, invoiced_qty, fulfillment_mode (IN_STOCK¦BACK_TO_BACK¦DROP_SHIP¦SPLIT), available_qty_at_confirm, deficit_qty, linked_po_id, selected_supplier_id, margin, margin_percent, status. Indexes per §17.2. | §4.1, §4.2 | demand | A29-P1-02, A29-P2-02 | 3 | — |
| A29-P3-05 | SaleOrder & SaleOrderLine Entities + EF Config | C# entities with enums (SaleOrderStatus, FulfillmentMode, DeliveryMode). EF config: HasQueryFilter(so => so.OrgId == _orgId), relationships to BusinessPartner, ProductVariant, logistics.Address. AutoMapper profiles. FluentValidation rules. | §4.1, §4.2 | demand | A29-P3-04 | 4 | TC-12 |
| A29-P3-06 | SaleOrder Service (CRUD + Document Numbering) | ISaleOrderService: Create (DRAFT, auto-generate so_number via existing document_number_sequences pattern, generate trace_id = Guid.NewGuid()), Update (DRAFT only), GetById, GetList with filters. Price auto-resolution on line add via IPricingService. Line total calculation. | §4.1, §4.2, §4.5 | demand | A29-P3-05, A29-P2-03 | 5 | TC-04, TC-05 |
| A29-P3-07 | SaleOrder API Controller | SaleOrdersController: GET/POST/PUT /api/sale-orders, GET /api/sale-orders/{id}, POST /api/sale-orders/{id}/confirm, POST /api/sale-orders/{id}/cancel, GET /api/sale-orders/{id}/timeline, GET /api/sale-orders/{id}/availability. | §4.5 | demand | A29-P3-06 | 3 | TC-04, TC-05, TC-12 |
| A29-P3-08 | SaleOrder Config Frontend | React: Sale Order Configuration admin page (SUPPLY_DEPT_ADMIN role). Toggle controls for auto_po, drop_ship, self_pickup. Supplier selection mode dropdown. Approval mode selector. Audit log viewer. | §3.2–§3.5 | — | A29-P3-03 | 2 | — |

# 6. Phase 4 — Availability Check, Reservation & Email Intimation

Priority: P0 — Critical Path | Estimated: 28 Hours (3.5 Days) | FSD Sections: 4.3–4.4, 5.1–5.3

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P4-01 | Extend IStockReservationService for SALES_ORDER | Add SALES_ORDER to ReservationSourceType enum. Extend Reserve() to accept SaleOrderLine source_id. Ensure FEFO multi-row allocation works for sales reservations. Add expiry support (expires_at from config TTL). No new table — uses existing inventory.stock_reservations. | §4.4 | inventory (shared) | A29-P3-05 | 4 | TC-04, TC-05 |
| A29-P4-02 | Three-Scenario Availability Check Service | IAvailabilityCheckService.CheckAndReserve(saleOrderId): For each SO line, check available_qty. Scenario 1 (IN_STOCK): full reserve via IStockReservationService. Scenario 2 (SPLIT): partial reserve + deficit. Scenario 3 (BACK_TO_BACK): full deficit. Scenario 4 (DROP_SHIP): no stock impact. Set line fulfillment_mode, available_qty_at_confirm, deficit_qty. | §4.3 | demand, inventory | A29-P4-01, A29-P3-06 | 6 | TC-04, TC-05, TC-06 |
| A29-P4-03 | SO Confirmation Orchestrator | Confirm SO transaction: validate DRAFT status, run availability check, reserve stock, create auto-POs for deficit (delegates to Phase 5), update SO status to CONFIRMED, enqueue email intimation via Hangfire. All in one transaction (except PO creation and email which are Hangfire jobs). | §4.3, §4.5 | demand | A29-P4-02 | 4 | TC-04, TC-05, TC-06 |
| A29-P4-04 | SO Cancellation Service | Cancel SO: validate status, release all ACTIVE reservations via IStockReservationService.Release(), cancel linked DRAFT POs, update SO status = CANCELLED, enqueue cancellation email. | §4.5 | demand, inventory | A29-P4-01 | 2 | — |
| A29-P4-05 | Reservation Expiry Hangfire Job | RecurringJob: scan stock_reservations WHERE source_type = SALES_ORDER AND status = ACTIVE AND expires_at < NOW(). Release expired reservations. Update SO line status. Send expiry warning email 24h before. | §4.4, §5.1 | inventory, demand | A29-P4-01 | 2 | — |
| A29-P4-06 | Create SaleOrderIntimations Table (Migration) | Create demand.SaleOrderIntimations: intimation_id, org_id, sale_order_id, event_type (SO_CONFIRMED¦PO_CREATED¦DROP_SHIP¦RESERVED¦PO_APPROVED¦GRN_RECEIVED¦EXPIRING), recipients, subject, body_html, sent_at, status (SENT¦FAILED¦QUEUED), error_message, hangfire_job_id. HasQueryFilter on org_id. | §5.3 | demand | A29-P3-04 | 1 | — |
| A29-P4-07 | Email Intimation Service & Templates | ISaleOrderEmailService: SendConfirmation(soId), SendPOCreated(soId, poId), SendDropShip(soId), SendReserved(soId), SendPOApproved(poId), SendGRNReceived(grnId), SendExpiring(reservationId). HTML templates with line-by-line breakdown table. Hangfire BackgroundJob.Enqueue with 3x retry. | §5.1, §5.2, §5.3 | demand | A29-P4-06, A29-P4-03 | 6 | TC-11 |
| A29-P4-08 | Availability & Email Unit Tests | Test: all 4 scenarios (in-stock, split, B2B, drop-ship), FEFO multi-batch reservation, expiry TTL, email template content validation, multi-tenant isolation of reservations. | §4.3–§4.4, §5 | demand, inventory | A29-P4-07 | 3 | TC-04, TC-05, TC-11, TC-12 |

# 7. Phase 5 — Back-to-Back PO & trace_id / Timeline Linkage

Priority: P1 — High | Estimated: 32 Hours (4 Days) | FSD Sections: 3.3–3.4, 6.1–6.4, 13.1–13.7

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P5-01 | Add PO Source & Linked Fields (Migration) | Add columns to procurement.PurchaseOrders: source NVARCHAR(20) DEFAULT 'MANUAL' (MANUAL¦BACK_TO_BACK¦DROP_SHIP¦MIR), linked_so_line_id BIGINT NULL, linked_so_id BIGINT NULL, customer_shipping_address_id BIGINT NULL FK to logistics.addresses, auto_generated_qty, auto_generated_price, auto_selected_supplier_id. Indexes per §17.2. | §6.3 | procurement | A29-P3-04 | 2 | — |
| A29-P5-02 | Supplier Selection Service | ISupplierSelectionService with 3 modes: DEFAULT_SUPPLIER (variant.default_supplier_id fallback to MANUAL), BEST_MATCH (composite score = Scorecard*0.6 + PriceRank*0.4, tiebreak on lead_time_days), MANUAL (create task for supply team). Mode read from SaleOrderConfig. | §3.3 | demand, suppliers | A29-P3-03, A29-P1-04 | 5 | TC-06 |
| A29-P5-03 | Auto-PO Creation Service | IAutoPurchaseOrderService.CreateFromSODeficit(soLineId, supplierId, qty, price): Create PO with source=BACK_TO_BACK or DROP_SHIP, linked_so_id/linked_so_line_id, trace_id from SO. PO status per config: DRAFT_ONLY→DRAFT, REQUIRE_WORKFLOW→PENDING_APPROVAL, AUTO_SEND→APPROVED. Store auto_generated_qty/price/supplier for audit. | §6.1, §6.2 | procurement, demand | A29-P5-01, A29-P5-02, A29-P2-03 | 6 | TC-05, TC-06, TC-07 |
| A29-P5-04 | trace_id Propagation (SO → PO) | In AutoPO creation: copy saleOrder.trace_id to newPO.trace_id. Enqueue Hangfire timeline event PO_CREATED_FROM_SO via existing _timelineService.AppendEvent. Ensure org_id passed explicitly to Hangfire job. | §6.3.1, §13.3 | workflow, procurement | A29-P5-03 | 3 | TC-13 |
| A29-P5-05 | Drop Ship PO Flow | When fulfillment_mode=DROP_SHIP and config.drop_ship_enabled: Create PO with customer_shipping_address_id = SO.shipping_address_id, source=DROP_SHIP. No warehouse stock impact. PO vendor ships directly to customer address. | §4.3 Scenario 4, §14.1 | procurement | A29-P5-03 | 2 | — |
| A29-P5-06 | GRN Auto-Reservation Link | Extend GRN approval service: after GRN for B2B PO (linked_so_line_id not null), auto-call IStockReservationService.Reserve(source_type=SALES_ORDER, source_id=soLineId) for received qty. Update SO line status OPEN→RESERVED. Enqueue GRN_FOR_SO_PO timeline event + email. | §6.4, §13.3 | procurement, inventory, demand | A29-P5-04, A29-P4-01 | 4 | TC-14 |
| A29-P5-07 | New Timeline Event Types | Add 7 event_type values to DocumentTimelines: SO_CREATED, SO_CONFIRMED, PO_CREATED_FROM_SO, GRN_FOR_SO_PO, SO_STOCK_RESERVED, SO_FULFILLED, SO_INVOICED. Extend existing TimelineService to emit these at each lifecycle point. | §13.3 | workflow | A29-P5-04 | 3 | TC-13, TC-14 |
| A29-P5-08 | Timeline Query API | Endpoints: GET /api/sale-orders/{id}/timeline, GET /api/purchase-orders/{id}/timeline (update existing), GET /api/timeline/{traceId}. Multi-tenancy enforced: org_id+trace_id unique index, org_id from JWT, Hangfire jobs pass org_id explicitly. | §13.5, §13.7 | workflow | A29-P5-07 | 2 | TC-13, TC-14, TC-15 |
| A29-P5-09 | B2B PO & Timeline Unit Tests | Test: 3 supplier selection modes, auto-PO creation with all 3 approval modes, trace_id propagation, GRN auto-reservation, timeline event chain (7+ events), non-blocking write (<2s confirm), multi-tenant timeline isolation. | §6, §13 | procurement, workflow | A29-P5-08 | 3 | TC-05, TC-06, TC-07, TC-13, TC-14, TC-15 |
| A29-P5-10 | Margin Calculation | On auto-PO creation: compute soLine.margin = selling_price - purchase_price, soLine.margin_percent. Stored on SaleOrderLines for reporting. | §14.2 | demand | A29-P5-03 | 1 | — |
| A29-P5-11 | PO Modification Tracking (Pre-Approval) | Track auto_generated_qty/price/supplier vs user-modified values on PO. Allow supply team to edit DRAFT B2B POs: update qty, supplier, price, add items, split PO. Audit log of changes. | §6.2 | procurement | A29-P5-03 | 1 | TC-07 |

# 8. Phase 6 — Fulfillment (Delivery Orders Integration)

Priority: P1 — High | Estimated: 24 Hours (3 Days) | FSD Sections: 7.1–7.9, 8.1–8.3

CRITICAL: This phase extends existing logistics.delivery_orders — it does NOT create new fulfillment tables.

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P6-01 | Extend delivery_orders for SALE_ORDER Source (Migration) | Add columns to logistics.delivery_orders: sale_order_id BIGINT NULL FK, delivery_mode NVARCHAR(15) NULL, pickup_person_name, pickup_person_id_type, pickup_person_id_number, pickup_person_id_authorization. Add SALE_ORDER to DeliverySourceType enum. Add so_line_id BIGINT NULL to delivery_order_lines. | §7.1 | logistics | A29-P3-04 | 2 | — |
| A29-P6-02 | DeliveryOrderService.CreateFromSaleOrder() | Extend existing from-source creation pattern: create delivery_order with from_source_type=SALE_ORDER, sale_order_id, delivery_mode (SHIP/SELF_PICKUP), ship_to_address_id from logistics.addresses, trace_id from SO. Create delivery_order_lines with so_line_id mapping. Use existing document_number_sequences for DO number. | §7.3 | logistics, demand | A29-P6-01, A29-P3-06 | 4 | TC-08, TC-09 |
| A29-P6-03 | Extend GoodsIssueService for SALE_ORDER Source | Add case DeliverySourceType.SALE_ORDER to PostsGoodsIssue: determine movement type (SALES_SHIP or SALES_HANDOVER based on delivery_mode). Consume reservation via IStockReservationService.Consume(). Update soLine.fulfilled_qty. Idempotent (existing pattern). | §7.5, §8.3 | logistics, inventory, demand | A29-P6-02, A29-P4-01 | 4 | TC-08, TC-09 |
| A29-P6-04 | Self-Pickup Completion Endpoint | POST /api/delivery-orders/{id}/pickup: record pickup_person_name, pickup_person_id_type/number, pickup_authorization. Validate delivery_mode=SELF_PICKUP. Post goods issue (SALES_HANDOVER). Advance status to DELIVERED. Generate gate pass PDF via QuestPDF (reuse existing packing list template). | §8.2, §8.3 | logistics | A29-P6-03 | 3 | TC-08 |
| A29-P6-05 | Sales Fulfillment Convenience APIs | POST /api/sale-orders/{id}/create-delivery: create DO from SO lines. GET /api/sale-orders/{id}/deliveries: list DOs for SO. All other operations use existing /api/delivery-orders/{id}/* endpoints (pick, pack, goods-issue, ship, track, deliver). | §7.8 | demand, logistics | A29-P6-02 | 2 | TC-09 |
| A29-P6-06 | SO Status Update on Fulfillment Completion | When delivery order reaches DELIVERED/COMPLETED: update SO line fulfilled_qty, check if all lines fulfilled → SO status PARTIALLY_FULFILLED or FULFILLED. Emit SO_FULFILLED timeline event. Send fulfillment email. | §7.6 | demand, workflow | A29-P6-03, A29-P5-07 | 3 | TC-09, TC-14 |
| A29-P6-07 | Fulfillment Integration Tests | Test: create DO from SO, pick/pack/goods-issue/deliver flow, self-pickup flow with gate pass, partial fulfillment (3 DOs from 1 SO), mixed delivery modes, SO status transitions, reservation consume on goods issue, multi-tenant isolation. | §7, §8 | logistics, demand, inventory | A29-P6-06 | 4 | TC-08, TC-09, TC-12 |
| A29-P6-08 | Fulfillment Frontend | React: SO detail page 'Create Delivery' button → line/qty selector → creates DO. Self-pickup form (person name, ID, authorization). Link to existing delivery order tracking pages. SO deliveries tab showing all DOs. | §7.8, §7.9 | — | A29-P6-05 | 2 | — |

# 9. Phase 7 — Sales Invoicing & Customer Finance

Priority: P1 — High | Estimated: 32 Hours (4 Days) | FSD Sections: 9.1–9.5, 10.1

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P7-01 | Create SalesInvoices & SalesInvoiceLines Tables (Migration) | Create finance.SalesInvoices: invoice_id, org_id, invoice_number, sale_order_id, partner_id, invoice_date, due_date, subtotal, tax_amount, discount_amount, grand_total, amount_paid, balance_due, status (DRAFT¦ISSUED¦PARTIALLY_PAID¦PAID¦OVERDUE¦CANCELLED¦CREDIT_NOTE), currency_code, trace_id. Create finance.SalesInvoiceLines. Indexes per §17.2. | §9.1, §9.2 | finance | A29-P3-04 | 2 | — |
| A29-P7-02 | Create CustomerPayments & PaymentAllocations Tables (Migration) | Create finance.CustomerPayments: payment_id, org_id, partner_id, payment_number, payment_date, amount, payment_method (CASH¦CHEQUE¦BANK_TRANSFER¦CARD¦ONLINE), cheque_number, bank_reference, currency_code, status (RECEIVED¦BOUNCED¦REVERSED). Create finance.PaymentAllocations: allocation_id, payment_id, invoice_id, allocated_amount. | §9.3, §9.4 | finance | A29-P7-01 | 2 | — |
| A29-P7-03 | Create CustomerLedger Table (Migration) | Create finance.CustomerLedger: entry_id, org_id, partner_id, entry_date, entry_type (INVOICE¦PAYMENT¦CREDIT_NOTE¦DEBIT_NOTE¦ADVANCE¦REFUND¦OPENING_BAL), reference_type, reference_id, reference_number, debit_amount, credit_amount, running_balance, currency_code, narration. Mirrors existing SupplierLedger pattern. Indexes per §17.2. | §10 | finance | A29-P1-02 | 2 | — |
| A29-P7-04 | SalesInvoice Entity, Service & Business Rules | ISalesInvoiceService: CreateFromFulfillment(doId) — only from DELIVERED/COMPLETED DOs. Validate: invoiced_qty <= delivered_qty. Multiple invoices per SO (partial invoicing). On ISSUE: write CustomerLedger DEBIT entry in SAME transaction. Copy trace_id from SO. Emit SO_INVOICED timeline event. | §9.5, §13.3 | finance, demand, workflow | A29-P7-01, A29-P6-06, A29-P5-07 | 6 | TC-14 |
| A29-P7-05 | CustomerPayment Service & Auto-Allocation | ICustomerPaymentService: RecordPayment(partnerId, amount, method, details). Auto-allocate FIFO (oldest unpaid invoice first) with manual override. On RECEIVED: write CustomerLedger CREDIT entry in SAME transaction. Update invoice amount_paid/balance_due. Auto-set PARTIALLY_PAID when amount_paid > 0, PAID when balance_due = 0. | §9.3, §9.4, §9.5 | finance | A29-P7-02, A29-P7-04 | 5 | — |
| A29-P7-06 | CustomerLedger Service | ICustomerLedgerService: AppendEntry(partnerId, type, debit, credit, reference). Running balance calculation: prev_balance + debit - credit. Append-only pattern (same as SupplierLedger). GetLedger(partnerId, dateRange) with pagination. | §10, §10.1 | finance | A29-P7-03 | 3 | — |
| A29-P7-07 | Invoice Overdue Hangfire Job | RecurringJob (daily): scan SalesInvoices WHERE status IN (ISSUED, PARTIALLY_PAID) AND due_date < TODAY. Set status = OVERDUE. | §9.5 | finance | A29-P7-04 | 1 | — |
| A29-P7-08 | Sales Invoice & Payment API Endpoints | SalesInvoicesController: CRUD, POST /issue, GET /pdf (QuestPDF). CustomerPaymentsController: POST, GET, POST /{id}/allocate. CustomerLedgerController: GET /api/partners/{id}/ledger (receivables). | §9.1–§9.5, §10 | finance | A29-P7-05, A29-P7-06 | 4 | — |
| A29-P7-09 | Invoice PDF Generation (QuestPDF) | Sales Invoice PDF: header (company, customer), line items table, totals, tax, payment terms, bank details. Gate Pass PDF (reuse from fulfillment). Both stored as document attachments. | §9.1 | finance | A29-P7-04 | 3 | — |
| A29-P7-10 | Invoicing & Payment Unit Tests | Test: invoice only against delivered qty, partial invoicing, payment auto-allocation FIFO, manual allocation, ledger running balance accuracy, overdue detection, multi-tenant isolation, bounced payment reversal. | §9, §10 | finance | A29-P7-08 | 4 | TC-12 |

# 10. Phase 8 — Product Ledger & Inventory Impact

Priority: P2 — Medium | Estimated: 16 Hours (2 Days) | FSD Sections: 11.1–11.4, 12.1–12.2

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P8-01 | Create ProductLedger Table (Migration) | Create finance.ProductLedger: entry_id, org_id, variant_id, product_id (denormalized), entry_date, entry_type (PURCHASE¦SALE¦RETURN_IN¦RETURN_OUT¦ADJUSTMENT¦WRITE_OFF), reference_type, reference_id, reference_number, partner_id, quantity, unit_cost, total_cost, direction (IN¦OUT), running_qty, running_value, narration. Indexes per §17.2. | §11.1 | finance | — | 2 | — |
| A29-P8-02 | ProductLedger Entity & Service | IProductLedgerService: AppendEntry(variantId, type, qty, unitCost, direction, reference). WAC calculation: on IN → new_value = prev_value + (qty*cost), new_WAC = new_value/new_qty. On OUT → COGS = current WAC. Written in SAME transaction as GRN approval or Invoice issuance. | §11.2, §11.3 | finance | A29-P8-01 | 5 | TC-10 |
| A29-P8-03 | Integrate ProductLedger with GRN & Sales Invoice | On GRN approval: write PURCHASE entry (IN, unit_cost = PO line price). On Sales Invoice issuance: write SALE entry (OUT, unit_cost = WAC, not selling price). Both in same transaction as business action. | §11.2 | finance, procurement, demand | A29-P8-02, A29-P7-04 | 3 | TC-10 |
| A29-P8-04 | Add Sales Movement Types to Existing MovementType Enum | Add SALES_SHIP, SALES_HANDOVER, SALES_RETURN, DROP_SHIP_VIRTUAL to existing MovementType enum used by GoodsIssueService. Note: stock_balances reserved_qty/available_qty already exist from IStockReservationService (G4 decision). | §12.1, §12.2 | inventory | A29-P6-03 | 1 | — |
| A29-P8-05 | ProductLedger API Endpoints | GET /api/product-ledger/{variantId}: paginated entries. GET /api/product-ledger/{variantId}/summary: total purchased, sold, current stock value, WAC. GET /api/reports/product-profitability: revenue vs COGS by product. | §11.4 | finance | A29-P8-02 | 2 | TC-10 |
| A29-P8-06 | Product Ledger Unit Tests | Test: WAC calculation across multiple GRNs at different prices, COGS on sale, running_qty/running_value accuracy, zero-stock edge case, multi-tenant isolation. | §11 | finance | A29-P8-03 | 3 | TC-10 |

# 11. Phase 9 — Reports & Frontend

Priority: P3 — Low | Estimated: 24 Hours (3 Days) | FSD Sections: 15, Frontend

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P9-01 | R1: Sales Order Register Report | GET /api/reports/sales/order-register: all SOs with status, totals, customer, delivery mode. Filters: date range, status, customer, delivery_mode. PDF (QuestPDF) + Excel export. | §15 R1 | reports | A29-P3-07 | 2 | — |
| A29-P9-02 | R2: Customer Ledger Report | GET /api/reports/sales/customer-ledger: receivables ledger per customer. Filters: customer, date range. | §15 R2 | reports | A29-P7-06 | 2 | — |
| A29-P9-03 | R3: Aging Receivables Report | GET /api/reports/sales/aging-receivables: outstanding invoices by age bucket (0-30, 31-60, 61-90, 90+ days). Filters: as-of date, customer. | §15 R3 | reports | A29-P7-04 | 2 | — |
| A29-P9-04 | R4–R6: Sales by Product, Customer, Fulfillment Status | Three reports: revenue/qty by product, revenue/count/avg by customer, open fulfillments by status/warehouse/delivery mode. All with PDF+Excel export. | §15 R4–R6 | reports | A29-P7-04, A29-P6-06 | 4 | — |
| A29-P9-05 | R7–R8: Margin Analysis & Sales vs Purchase | Margin Analysis: selling price vs cost, margin% by product/customer/SO. Sales vs Purchase Comparison: revenue vs COGS, gross margin by period. | §15 R7–R8 | reports | A29-P8-02, A29-P5-10 | 3 | — |
| A29-P9-06 | R9–R10: Product Ledger & Profitability Reports | Product Ledger Report: all movements per product with running qty/value. Product Profitability: revenue - COGS per product, ranked by margin. | §15 R9–R10 | reports | A29-P8-05 | 3 | — |
| A29-P9-07 | Sale Order Frontend Pages | React: SO list page with status filters. SO create/edit form with line items, customer selector, delivery mode toggle. SO detail page with tabs: Lines, Deliveries, Invoices, Payments, Timeline. Confirm/Cancel actions. | §4.5, §7.8 | — | A29-P3-07, A29-P6-05 | 4 | — |
| A29-P9-08 | Sales Invoice & Payment Frontend | React: Invoice list/detail pages. Create invoice from delivery. Invoice PDF viewer. Payment recording form with method selector. Payment allocation UI. Customer ledger view. | §9, §10 | — | A29-P7-08 | 3 | — |
| A29-P9-09 | Reports Dashboard Frontend | React: Sales Reports dashboard with all 10 reports. Filter controls, PDF download, Excel export. Chart visualizations for margin and aging reports. | §15 | — | A29-P9-06 | 1 | — |

# 12. Phase 10 — Integration Testing & Acceptance

Priority: P1 — High | Estimated: 12 Hours (1.5 Days) | FSD Section: 17

| Task ID | Task Title | Description | FSD Ref | Schema(s) | Depends On | Est. Hours | Test IDs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A29-P10-01 | TC-01: Vendor Backward Compatibility | Verify: GET /api/suppliers returns only is_vendor=1. Create PO with existing vendor. All procurement flows unchanged after rename. | §17 TC-01 | suppliers, procurement | A29-P1-07 | 1 | TC-01 |
| A29-P10-02 | TC-04/05: SO In-Stock & SPLIT Scenarios | Test full flow: SO with 50 available → reserve all (TC-04). SO with 60/100 available → 60 reserved + PO for 40 (TC-05). Verify email content, reservation records, PO creation. | §17 TC-04, TC-05 | demand, inventory, procurement | A29-P4-08, A29-P5-09 | 2 | TC-04, TC-05 |
| A29-P10-03 | TC-08: Self-Pickup Full Flow | Test: SO with SELF_PICKUP → DO created → pick → pack → goods issue (SALES_HANDOVER) → record pickup person → DELIVERED. Verify gate pass PDF, stock deduction, no consignment. | §17 TC-08 | logistics, demand, inventory | A29-P6-07 | 1 | TC-08 |
| A29-P10-04 | TC-09: Partial Fulfillment (3 DOs) | Test: SO for 100 units → DO-1 (40 shipped) → DO-2 (30 shipped) → DO-3 (30 self-pickup). Verify SO status transitions: CONFIRMED→PARTIALLY_FULFILLED→FULFILLED. Mixed delivery modes. | §17 TC-09 | logistics, demand | A29-P6-07 | 1 | TC-09 |
| A29-P10-05 | TC-10: Product Ledger WAC Accuracy | Test: GRN 100@$10 → Sell 30@$15. Verify PURCHASE entry (IN), SALE entry (OUT, COGS=WAC=$10). Running_qty=70, running_value=$700. | §17 TC-10 | finance | A29-P8-06 | 1 | TC-10 |
| A29-P10-06 | TC-12: Multi-Tenant Isolation | Test: Create customer in Org A. Login as Org B. Verify: cannot access Org A customer, cannot reference in SO, timeline events isolated, reservations isolated, invoices isolated. | §17 TC-12 | all | A29-P7-10 | 2 | TC-12 |
| A29-P10-07 | TC-13/14: trace_id Full Chain Test | Test: SO confirmed (SPLIT) → auto-PO → PO approved → GRN → auto-reserve → 2 DOs → invoices. GET /api/timeline/{traceId}: verify all 7+ events chronologically. Verify trace_id identical across all documents. | §17 TC-13, TC-14 | workflow, all | A29-P5-09, A29-P7-10 | 2 | TC-13, TC-14 |
| A29-P10-08 | TC-15: Timeline Non-Blocking Write | Test: Confirm SO that triggers auto-PO. Measure: SO confirmation response < 2 seconds. Timeline event appears within 5 seconds (async via Hangfire). Verify business transaction not slowed. | §17 TC-15 | workflow | A29-P5-08 | 1 | TC-15 |
| A29-P10-09 | End-to-End Smoke Test | Full cycle: Create customer → Create SO → Confirm (SPLIT) → Approve auto-PO → Receive GRN → Create DO → Pick → Pack → Goods Issue → Ship → Deliver → Invoice → Payment → Verify ledgers + timeline + reports. | §17 | all | A29-P10-07 | 1 | All |

# 13. Dependency Graph

Critical path is highlighted. Tasks within a phase can be parallelized where dependencies allow.

Phase 1: Business Partner Migration (P0)

A29-P1-01 → A29-P1-02 → A29-P1-03 → A29-P1-04 → A29-P1-05 → A29-P1-06 → A29-P1-07

└→ A29-P1-08 (parallel)

Phase 2: Product & Pricing (P1) — starts after A29-P1-02

A29-P2-01 ─┐

A29-P2-02 ─┤→ A29-P2-03 → A29-P2-04 → A29-P2-05

└→ A29-P2-06 (parallel)

Phase 3: Sale Order Core (P0) — starts after P1 + P2

A29-P3-01 → A29-P3-02 → A29-P3-03 → A29-P3-08 (parallel)

A29-P3-04 → A29-P3-05 → A29-P3-06 → A29-P3-07

Phase 4: Availability & Email (P0) — starts after P3

A29-P4-01 → A29-P4-02 → A29-P4-03 → A29-P4-07

A29-P4-04 (parallel after P4-01)

A29-P4-05 (parallel after P4-01)

A29-P4-06 → A29-P4-07 → A29-P4-08

Phase 5: B2B PO & Timeline (P1) — starts after P3 + P4

A29-P5-01 → A29-P5-02 → A29-P5-03 → A29-P5-04 → A29-P5-07 → A29-P5-08 → A29-P5-09

└→ A29-P5-05 (parallel)

└→ A29-P5-10 (parallel)

└→ A29-P5-11 (parallel)

A29-P5-06 (after P5-04 + P4-01)

Phase 6: Fulfillment / Delivery (P1) — starts after P3 + P4

A29-P6-01 → A29-P6-02 → A29-P6-03 → A29-P6-04

└→ A29-P6-05 → A29-P6-08 (parallel)

A29-P6-06 (after P6-03 + P5-07)

A29-P6-07 (after P6-06)

Phase 7: Invoicing & Finance (P1) — starts after P6

A29-P7-01 → A29-P7-04 → A29-P7-09 (parallel)

A29-P7-02 → A29-P7-05

A29-P7-03 → A29-P7-06

A29-P7-07 (after P7-04)

A29-P7-08 (after P7-05 + P7-06) → A29-P7-10

Phase 8: Product Ledger (P2) — starts after P7

A29-P8-01 → A29-P8-02 → A29-P8-03 → A29-P8-06

A29-P8-04 (after P6-03)    A29-P8-05 (after P8-02)

Phase 9: Reports & Frontend (P3) — starts progressively

A29-P9-01..06 (after respective data phases)

A29-P9-07..09 (after respective API phases)

Phase 10: Integration Testing (P1) — starts after all phases

A29-P10-01..09 (after all dependent phases)

# 14. Effort Summary by Phase

| Phase | Title | Tasks | Hours | Days | Priority |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | Business Partner Migration | 8 | 32 | 4.0 | P0 |
| Phase 2 | Product & Pricing | 6 | 16 | 2.0 | P1 |
| Phase 3 | Sale Order Core | 8 | 24 | 3.0 | P0 |
| Phase 4 | Availability, Reservation & Email | 8 | 28 | 3.5 | P0 |
| Phase 5 | B2B PO & trace_id Linkage | 11 | 32 | 4.0 | P1 |
| Phase 6 | Fulfillment (Delivery Orders) | 8 | 24 | 3.0 | P1 |
| Phase 7 | Sales Invoicing & Finance | 10 | 32 | 4.0 | P1 |
| Phase 8 | Product Ledger & Inventory | 6 | 16 | 2.0 | P2 |
| Phase 9 | Reports & Frontend | 9 | 24 | 3.0 | P3 |
| Phase 10 | Integration Testing | 9 | 12 | 1.5 | P1 |
|  | TOTAL | 83 | 240 | 30.0 |  |

## Effort by Work Type

| Work Type | Approximate Hours | % of Total |
| --- | --- | --- |
| Migrations (EF Core) | 20 | 8% |
| Entities & EF Config | 25 | 10% |
| Services & Business Logic | 65 | 27% |
| API Controllers | 25 | 10% |
| Integration (Extend Existing) | 20 | 8% |
| Frontend (React) | 17 | 7% |
| Unit & Integration Tests | 35 | 15% |
| Reports & PDFs | 20 | 8% |
| Hangfire Jobs | 5 | 2% |
| End-to-End Testing | 8 | 3% |

# 15. Risk Register

| ID | Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | BusinessPartner rename breaks existing FK references | High | Medium | Careful sp_rename order. Run all existing procurement tests after migration. Backward-compat aliases. |
| R2 | IStockReservationService FEFO allocation race condition under concurrent SO confirmations | High | Low | Existing RowVersion concurrency on stock_reservations. Unit test with parallel reservations. |
| R3 | delivery_orders state machine assumes PO/SRO source — SALE_ORDER source may hit unexpected validations | Medium | Medium | Review all state transition guards for source-type assumptions. Add SALE_ORDER to all relevant switch statements. |
| R4 | GoodsIssueService PostsGoodsIssue does not handle SALES_HANDOVER movement type | Medium | Low | Extend switch with explicit case. Unit test both SALES_SHIP and SALES_HANDOVER paths. |
| R5 | Auto-PO creation in SO confirmation transaction causes long-running transaction | High | Medium | PO creation via Hangfire BackgroundJob.Enqueue (non-blocking). Only reservation is in main transaction. |
| R6 | Product Ledger WAC calculation drift from rounding | Low | Medium | Use DECIMAL(18,4) everywhere. Test with multi-GRN scenarios. Periodic reconciliation report. |
| R7 | Email intimation Hangfire job failures not surfaced to users | Medium | Low | 3x retry with exponential backoff. FAILED status logged in SaleOrderIntimations. Admin alert on repeated failures. |
| R8 | Existing 1531 logistics tests break after delivery_orders schema changes | High | Low | All new columns are NULL-able additions. Existing tests should pass unchanged. Run full logistics test suite after migration. |

# 16. Migration Script Execution Order

Execute in sequence. Each migration is independently revertible with dotnet ef database update <previous>.

| # | Migration Name | Phase | Schema(s) | Description |
| --- | --- | --- | --- | --- |
| M01 | RenameSupplierToBusinessPartner | P1 | suppliers | Rename table + PK column, update FKs |
| M02 | AddPartnerTypeFlagsAndCarrierFields | P1 | suppliers | Add type flags, carrier/service fields |
| M03 | AddDefaultSupplierToVariants | P2 | inventory | Add default_supplier_id to ProductVariants |
| M04 | CreatePricingRules | P2 | inventory | New PricingRules table |
| M05 | CreateSupplyDeptAdminRole | P3 | auth | New role + permissions seed |
| M06 | CreateSaleOrderConfig | P3 | demand | New SaleOrderConfig table |
| M07 | CreateSaleOrderTables | P3 | demand | SaleOrders + SaleOrderLines tables |
| M08 | AddSalesOrderToReservationSourceType | P4 | inventory | Extend ReservationSourceType enum |
| M09 | CreateSaleOrderIntimations | P4 | demand | New SaleOrderIntimations table |
| M10 | AddPOSourceAndLinkedFields | P5 | procurement | Add source, linked_so_id, etc. to POs |
| M11 | AddSOTimelineEvents | P5 | workflow | Register 7 new event types |
| M12 | ExtendDeliveryOrdersForSaleOrderSource | P6 | logistics | Add sale_order_id, delivery_mode, pickup fields to DOs |
| M13 | CreateSalesInvoiceTables | P7 | finance | SalesInvoices + SalesInvoiceLines |
| M14 | CreateCustomerPaymentTables | P7 | finance | CustomerPayments + PaymentAllocations |
| M15 | CreateCustomerLedger | P7 | finance | New CustomerLedger table |
| M16 | CreateProductLedger | P8 | finance | New ProductLedger table |

Total: 16 migrations across 6 schemas (suppliers, inventory, auth, demand, procurement, workflow, logistics, finance).

## 16.1 Rollback Strategy

- Each migration is separate and revertible: dotnet ef database update <previous-migration>

- M01 (BusinessPartner rename): reversible by renaming table back to Suppliers

- M02–M04: nullable column additions, safe to drop

- M05–M09: new tables only, safe to drop without affecting existing data

- M10: nullable column additions to PurchaseOrders, safe to drop

- M11: additive to DocumentTimelines event types (no destructive impact)

- M12: nullable column additions to delivery_orders, safe to drop

- M13–M16: new tables only, safe to drop

- SALES_ORDER removal from ReservationSourceType requires clearing sales reservations first

- All 1531 existing logistics tests must pass after M12