# Task Breakdown — User–Supplier Access & Return Order Acknowledgment

Source: System Addendum v1.0

Date: 26 August 2026

Sizing is rough (S ≈ ½–1 day, M ≈ 1–2 days, L ≈ 3+ days) and should be re-estimated by the team. Type: DB = data/schema, BE = backend/API, FE = frontend/UI, QA = testing, SEC = security.

# Epic 1 — Supplier Type on User Creation (REQ-1.x)

| ID | Type | Task | Refs | Depends on | Size |
| --- | --- | --- | --- | --- | --- |
| T1.1 | DB | Add supplier_type (enum: Internal/External) to the user table + migration | 1.1, 1.4 | – | S |
| T1.2 | BE | Include Supplier Type in create/update user API; make it required and validate the value | 1.1, 1.3 | T1.1 | S |
| T1.3 | FE | Add "Supplier Type" dropdown (Internal/External) to Add/Edit User form with required-field validation | 1.1, 1.2, 1.3 | T1.2 | S |
| T1.4 | FE | Show Supplier Type on user view; persist and repopulate on edit | 1.4 | T1.3 | S |
| T1.5 | FE | Add Supplier Type column + filter to the user listing/grid | 1.5 | T1.2 | S |
| T1.6 | QA | Test: cannot save without type; value persists on reopen; grid filter works | 1.1–1.5 | T1.3–T1.5 | S |

# Epic 2 — User-to-Supplier Access Mapping (REQ-2.x)

| ID | Type | Task | Refs | Depends on | Size |
| --- | --- | --- | --- | --- | --- |
| T2.1 | DB | Create user_supplier mapping table (many-to-many) + migration | 2.1 | – | S |
| T2.2 | BE | API to read/save a user's supplier mappings as part of user save | 2.1, 2.4 | T2.1 | M |
| T2.3 | BE | Central access filter: restrict supplier queries/lists to the current user's mapped suppliers | 2.2 | T2.2 | M |
| T2.4 | BE/SEC | Server-side authorization guard on all supplier-scoped endpoints — deny access to non-mapped suppliers by direct ID/URL | 2.3 | T2.2 | M |
| T2.5 | FE | Multi-select supplier assignment on the user screen | 2.1, 2.4 | T2.2 | M |
| T2.6 | FE | Apply mapping filter to every supplier list/dropdown across the app (return orders, dispatch, reports) | 2.2 | T2.3 | M |
| T2.7 | QA/SEC | Test: user sees only mapped suppliers; removing a mapping revokes access immediately; direct-ID access to a non-mapped supplier is denied | 2.2–2.4 | T2.3–T2.6 | M |

⚠ Blocked/affected by open questions #1 & #2 (whether Supplier Type constrains which suppliers can be mapped). Confirm before T2.5.

# Epic 3 — Return Order Dispatch & Supplier Acknowledgment (REQ-3.x)

| ID | Type | Task | Refs | Depends on | Size |
| --- | --- | --- | --- | --- | --- |
| T3.1 | DB | Create acknowledgment-token table (token, return_order_id, supplier_id, created_at, expires_at, used_at, ack remarks/received date) + migration | 3.5, 3.7–3.9 | – | S |
| T3.2 | BE | Generate a unique, non-guessable token on dispatch; set expires_at from the configured expiry (Epic 4) | 3.5, 3.9 | T3.1, T4.2 | M |
| T3.3 | BE | Email service: compose dispatch email (return ref, item list, courier, tracking, dispatch date/remarks) + acknowledgment link | 3.1–3.3 | T3.2 | M |
| T3.4 | FE | Design responsive dispatch email template | 3.2, 3.3, §7 | T3.3 | S |
| T3.5 | BE | Public acknowledgment endpoint (no auth): validate token, check expiry, check not-already-used | 3.4, 3.5, 3.8, 3.10 | T3.2 | M |
| T3.6 | FE | Public acknowledgment page (no login): show items/details, confirm control, optional remarks + received date | 3.4, 3.6 | T3.5 | M |
| T3.7 | BE | On submit: record acknowledgment, mark token used, update return order status | 3.7, 3.8 | T3.5 | M |
| T3.8 | FE | "Link expired" and "already acknowledged" states on the public page | 3.8, 3.10 | T3.5 | S |
| T3.9 | FE | Show acknowledgment status + who/when/remarks on the internal return order view | 3.7 | T3.7 | S |
| T3.10 | SEC | Security review of the login-free link: token entropy, single-use enforcement, rate limiting/abuse protection, no data leakage beyond the one order | 3.4, 3.5, 3.8 | T3.5 | S |
| T3.11 | QA | E2E test: dispatch → email with correct details → acknowledge without login → status updates; expired link blocked; reuse blocked | 3.1–3.10 | T3.3–T3.9 | M |

⚠ Affected by open questions #3 (re-send on expiry), #5 (single-use — assumed yes), #6 (partial vs whole-dispatch acknowledgment). Confirm #6 before T3.6/T3.7 as it changes the page and data model.

# Epic 4 — Application Settings: Acknowledgment Link Expiry (REQ-4.x)

| ID | Type | Task | Refs | Depends on | Size |
| --- | --- | --- | --- | --- | --- |
| T4.1 | DB | Add acknowledgment-link expiry setting to app settings/config store + default value | 4.1, 4.4 | – | S |
| T4.2 | BE | Read the expiry setting when generating a token; validate range; fall back to default | 4.2–4.4 | T4.1 | S |
| T4.3 | FE | Settings UI field for expiry duration with validation (positive, min/max) | 4.1, 4.2, 4.4 | T4.1 | S |
| T4.4 | QA | Test: changing the value changes new links’ validity; invalid values rejected; default applied | 4.1–4.4 | T4.2, T4.3 | S |

⚠ Open questions #4 (unit: hours/days) and #7 (who can edit the setting) affect T4.1/T4.3.

# Epic 5 — Cross-Cutting

| ID | Type | Task | Refs | Size |
| --- | --- | --- | --- | --- |
| T5.1 | – | Resolve open questions #1–#7 with stakeholders (blocks several tasks) | §9 | S |
| T5.2 | QA | Full regression + end-to-end run of the combined flow | all | M |
| T5.3 | – | Update user/admin documentation and release notes | all | S |

# Suggested Sequence

- T5.1 — resolve open questions (unblocks the rest).

- Epic 1 (self-contained, quick win).

- Epic 4 (expiry setting) — needed before Epic 3 token generation.

- Epic 2 (access mapping).

- Epic 3 (dispatch + acknowledgment) — the largest epic, depends on Epic 4.

- T5.2 / T5.3 — regression, docs, release.

# Open Questions to Resolve First

- Does Supplier Type drive behaviour or just classify?

- Can a user map suppliers of both types or only a matching type?

- On link expiry, can internal users re-send a new link (and is it logged)?

- Expiry unit — hours, days, or both?

- Is the link single-use? (assumed yes)

- Partial item acknowledgment, or whole-dispatch only?

- Who can change the expiry setting — all users or admin only?